## Cover
TEST PLAN
Project Name | Website hỗ trợ kiểm tra kiến thức Quizizz |  |  | Reviewer | Trương Hoàng Vi
Project Code | Quizizz |  |  | Review date | 2022-01-25
Creator | Trương Hoàng Vi |  |  | Approver | Trần Thị Thanh Nga
Version | v1.0 |  |  | Approval Date
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2021-12-28 | v1.0 | Initial | A
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Group22_SRS_v3_0 |  |  |  | 3.0
Note on E10: ====== ID#AAAAUYIhIN8 (2022-01-18 06:48:02) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with the highest priority first, then increase gradually.
| 2 | Software is correct with software requirement specification
| 3 | The system runs smoothly on web browsers (Google, Firefox, ...)
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | A specific holiday shuts down both development and testing | Tet holiday, national day, International Workers’ Day,...
| 2 | When a defect is introduced that cannot allow any further testing
| 3 | When there are any network and hardware problems, we can suspend testing
| 4 | If we got more pending requests from the development team
| 5 | If the defect backlog continually increases over a two week period
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved
| 2 | When the holiday is over
| 3 | The contract is renegotiated with the client to extend delivery

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Leader
2 | Create test design |  |  | Members
3 | Create test cases |  |  | Members
4 | Create test data |  |  | Members
5 | Execute system test |  |  | Members
6 | Defects list |  |  | Members
7 | Create test report |  |  | Leader
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | SRS document | 2022-02-12 | Test leader | Test manager, team, customer
2 | Test plan | 2022-02-12 | Test leader | Test manager, team, customer | This document itself
3 | Test cases | 2022-02-12 | Test leader | Test manager, team, customer
4 | Defect logs | 2022-02-12 | Test leader | Test manager, team, customer
5 | Test report | 2022-02-12 | Test leader | Test manager, team, customer
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Members are inexperienced in software testing |  | Open training course to skill up your members |  | 1. Contact a training organization 2. Attend mandatory training 3. Quality test
2 | A team member suddenly quits work |  | Review and improve the team's working environment |  | 1. Consider the reason for leaving the job 2. Contact other testing teams to borrow members 3. Support the member who borrowed from another team to get the job done
2 | The development team edited the code of the project which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight to complete the project on time |  | Execute test cases with high to low priority or recruit new members to keep up with the work progress |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Team members didn't understand or misunderstood requests |  | Create a meeting to review and analyze requirements for members |  | 1. Create a meeting 2. Review required 3. Answer questions from members
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | Urging employees to work
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E33: ====== ID#AAAAUYIhIOA (2022-01-18 06:48:02) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G33: ====== ID#AAAAUYIhIN4 (2022-01-18 06:48:02) steps would have to be done if the risk were to become reality
Note on B43: ====== ID#AAAAUYIhIOI It can be (2022-01-18 06:48:02) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of Knowledge test support website described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | Groub22_SRS_v3_0.pdf
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, PC
OS | Window 10 64 bit Mac10.14.5 or heigher
Software | Quizizz |  |  |  | website
Database | SQL Server
Browser | Chrome Firefox Edge
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAUYIhIOE (2022-01-18 06:48:02) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 18130279 - Trương Hoàng Vi | Leader | Assigning works for members.Writing "Sign up", "Log in", "Edit profile" function in "SRS" document. Creating and managing a test plan. Creating a test report. Analyzing, designing and writing test cases, executing test and logging bugs for the "Login" and "Edit profile" function.
2 | 18130004 - Trương Nguyễn Thiên Ân | Member | Writing "Forgot password", "New lesson", "Print lesson" function in "SRS" document. Managing test plan. Analyzing, designing and writing test cases, executing test and logging bugs for "New lesson" function.
3 | 18130094 - Huỳnh Gia Huy | Member | Writing "Create quiz", "Play quiz" function in "SRS" document. Managing test plan. Analyzing, designing and writing test cases, executing test and logging bugs for the "Create quiz" function (incluse: Create and Setup).
4 | 18130144 - Lê Diễm My | Member | Writing "Notify", "Create collection", "Settings" function in "SRS" document. Managing test plan. Analyzing, designing and writing test cases, executing test and logging bugs for the "Create collection" function.
5 | 18130063 - Phạm Văn Hà | Member | Writing "Search", "Create a class", "Delete report" function in "SRS" document. Managing test plan. Analyzing, designing and writing test cases, executing test and logging bugs for the "Search" function.
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2021-12-28 | 2022-01-05
2 | Create test design | 2022-01-06 | 2022-01-10
3 | Create test case | 2022-01-11 | 2022-01-20
4 | Execute test and log bugs | 2022-01-21 | 2022-01-25
5 | Evaluate exit criteria & Test report | 2022-01-26 | 2022-01-30
6 | Review | 2022-01-31 | 2022-01-31
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 8
| Create test design | 8 | 4
| Create test case | 12 | 9
| Execute test and log bugs | 21 | 4
| Evaluate exit criteria & Test report | 25 | 4
| Review | 29 | 1
Detail Schedule

## Detail Schedule
# | Item | Responsibilities | December |  |  |  | January
|  |  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Team | bar: December 28
2 | Create test design | bar: January 6
2.1 | Edit profile | Trương Hoàng Vi | bar: January 6
2.2 | Log in | Trương Hoàng Vi
2.3 | Create quiz --> Setup | Huỳnh Gia Huy
2.4 | Create quiz --> Create | Huỳnh Gia Huy
2.5 | New lesson | Trương Nguyễn Thiên Ân
2.6 | Search | Phạm Văn Hà
2.7 | Create collection | Lê Diễm My
2.8 | Review | Team | bar: January 10
3 | Create test case | bar: January 11
3.1 | Edit profile | Trương Hoàng Vi | bar: January 11
3.2 | Log in | Trương Hoàng Vi
3.3 | Create quiz --> Setup | Huỳnh Gia Huy
3.4 | Create quiz --> Create | Huỳnh Gia Huy
3.5 | New lesson | Trương Nguyễn Thiên Ân
3.6 | Search | Phạm Văn Hà
3.7 | Create collection | Lê Diễm My
3.8 | Review | Team | bar: January 20
4 | Execute test and log bugs | bar: January 21
4.1 | Edit profile | Trương Hoàng Vi | bar: January 21
4.2 | Log in | Trương Hoàng Vi
4.3 | Create quiz --> Setup | Huỳnh Gia Huy
4.4 | Create quiz --> Create | Huỳnh Gia Huy
4.5 | New lesson | Trương Nguyễn Thiên Ân
4.6 | Search | Phạm Văn Hà
4.7 | Create collection | Lê Diễm My
4.8 | Review | Team | bar: January 25
5 | Evaluting exit criteria & Test report | Team | bar: January 26
6 | Review | Team | bar: January 31

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14

## EvaluateMember
ID - Name | Position | Evaluate | Percent
18130279 - Trương Hoàng Vi | Leader | Good | 100%
18130004 - Trương Nguyễn Thiên Ân | Member | Good | 100%
18130094 - Huỳnh Gia Huy | Member | Good | 100%
18130144 - Lê Diễm My | Member | Good | 100%
18130063 - Phạm Văn Hà | Member | Good | 95% | Not enough 10 defects